E.6	Annual Update – 2022

City of Minot: Annual Hazard Mitigation Plan Progress Report

6.1	Overview of Ward County, ND Hazard Mitigation Plan

6.2	Annual Progress Report Preparation

6.2.1	Report Preparation Methodology

6.2.2	Submission to Minot, ND City Council

6.2.3	Local Media Release of Annual Progress Report

6.2.4	Public Availability

6.3	Mitigation Goals and Action Item Review

6.3.1	Goal 01: Reduce the Effects of Hazards throughout the Planning Area

6.3.2	Goal 02: Increase Public and Local Leadership Awareness of Hazard

6.3.3	Goal 03: Protect Public Health and Safety Before, During, and After Hazard Events

6.3.4	Goal 04: Ensure Post-Disaster Operability of Critical Assets and Infrastructure

6.3.5	Goal 05: Provide Long-Term Mitigation Solutions to Vulnerable Areas

6.1	Overview of Ward County, ND Hazard Mitigation Plan

In 2013, the Ward County, ND Hazard Mitigation Plan (the Plan) was prepared by 12 local jurisdictions incorporated into Ward County. The Plan is organized to parallel the structure provided in the IFR, and to reflect the changes in the review process that were implemented in October 2012, with the enactment of the Local Mitigation Plan Review Guide. For the ease of review and use, the 2013 Plan was significantly reformatted from the 2008 Plan.

On October 7, 2013 the Plan was formally adopted by the Minot City Council. Documentation of this adoption is provided in the original Plan. Original copies of the 2013 Plan, as well as the 2018 update, are available on the Ward County Emergency Management web page for public use. City of Minot employees in the Engineering, Planning, and Public Works Departments also have access to the Plan through an internal server dedicated to City projects.

In order to maintain compliance with the Federal Emergency Management Agency (FEMA), the Plan is updated every 5 years and submission of the update was due on October 1, 2018. The 2018 update to the Plan was approved by FEMA as documented by a letter to the North Dakota Department of Emergency Services dated August 17, 2018.

As a participating jurisdiction in Ward County, the City of Minot has prepared this evaluation for use by the Ward County Emergency Management Director (EMD), who is primarily responsible for monitoring the Plan. The EMD may use this document in preparing the County-wide annual evaluation report.

6.2	Annual Progress Report Preparation

To maintain the effectiveness of the Plan, a yearly evaluation report is used as a method of monitoring the Plan. This section explains the details of the report and components of the evaluation.

6.2.1	Report Preparation Methodology

Primary responsibility for the preparation of this report was given to the City of Minot Engineering Department, due to the department’s familiarity with ongoing Hazard Mitigation projects, as well as the City’s involvement in the Community Rating System (CRS) program. Evaluation of the Plan included input from the departments and personnel listed in the table below.

| 2017 Annual Evaluation Report Involvement |  |  |  |  |
| --- | --- | --- | --- | --- |
| Department | Contact Name | Contact Title | Contact Phone | Contact E-mail |
| Engineering | Lance Meyer | City Engineer | 701-857-4100 | Lance.meyer@minotnd.org |
| Engineering | Aleesha Erickson | GIS Coordinator | 701-857-4100 | Aleesha.erickson@minotnd.org |
| Public Works | Dan Jonasson | Public Works Director | 701-857-4140 | Dan.jonasson@minotnd.org |
| Public Information | Derek Hackett | Public Information Officer | 701-857-4727 | Derek.hackett@minotnd.org |

6.2.2	Submission to Minot, ND City Council

This report will be submitted to the Minot City Council on January 18, 2022 at 5:30 pm in City Council Chambers. A copy of this document will be filed for the Council’s records.

6.2.3	Local Media Release of Annual Progress Report

This report will be made available to the Minot Daily News, as well as the local TV stations.

6.2.4	Public Availability

The City of Minot’s Floodplain Management website has a copy of this report available to the public. This report is available in print at the City Public Works Building and the Minot Public Library.

6.3	Mitigation Goals and Action Item Review

Hazard assessments and mitigation strategies are located in a separate section of the Plan for each jurisdiction. Section 12 of the Plan consists of the hazard assessments, mitigation goals, and mitigation goal actions for the City of Minot. For each mitigation goal established, one or more action items were identified. While the mitigation goals are broad and encompass many components, each action item is limited in scope to a specific area of interest or department.

6.3.1	Goal 01: Reduce the Effects of Hazards throughout the Planning Area

Action 1: Continue to enforce floodplain management ordinance and practices

This action item has been accomplished and will be ongoing as part of the Plan.

Action 2: Strengthen floodplain ordinance to require additional elevations for new development

The City of Minot adopted a Flood Protection ordinance in 2015 that requires one foot of freeboard for residential structures in the SFHA. Non-residential structures may use flood-proofing options but must provide two feet of freeboard. The ordinance includes many other requirements for floodplain development to protect people and property in Minot and meet the minimum NFIP requirements. In 2020, the ordinance was revised to specifically state that utilities must meet freeboard requirements. Definitions of several items related to mobile home parks were added to the ordinance as well, in order to maintain consistency with the State’s model floodplain ordinance. Enforcement of the ordinance will continue as part of the Plan, and the freeboard requirement may be increased to three feet in the future.

Action 3: Consider joining the NFIP’s Community Rating System (CRS)

The City of Minot began participating in the CRS program in October 2016 as a Class 9 community. After further review, credited was received for additional activities and Minot was modified to a Class 8 in May 2017 and then to a Class 6 in November 2021. This action has been completed and will not be carried forward as part of the 2018 Plan update.

Action 4: Maintain membership in CRS and work towards decreasing rating and premiums for policyholders

Work was completed to increase the City of Minot’s rating in the CRS program by maximizing the credit received for existing activities. The Engineering Department completed the class modifications in 2021. These changes allowed the City of Minot to change from a Class 8 to a Class 6. This provides citizens of Minot in high risk flood areas with a 20 percent discount on flood insurance premiums. The renewal will be completed to keep the City of Minot at a Class 6 rating.

6.3.2	Goal 02: Increase Public and Local Leadership Awareness of Hazard, Risks, and Vulnerabilities; Increase Support for Mitigation Activities through Awareness

Action 1: Continue public information and outreach program to educate leaders, residents and business owners about hazards and mitigation

Various departments and local agencies have increased outreach efforts in the community since the Plan was adopted in 2013. The City’s participation in the CRS program has provided more awareness and information available to the community through several credited activities. The actions in Minot that support this goal include the following:

- A newsletter about flood preparedness and mitigation actions is sent annually to all residents who receive a water bill from the City.

- Properties in identified repetitive loss areas receive additional information each fall regarding flood risk in the area.

- In July 2017, a public open house was held for residents of Ward County to learn about several flood-related items, including flood risk on individual properties, flood insurance options, and preliminary FIRM maps that were published in June.

- FEMA’s High Water Mark Initiative was implemented in Minot in June 2018, and 15 signs throughout the community help residents understand the magnitude of the flood risk faced by the City.

- Residents can sign up for emergency notifications through the City’s website.

- Flyers are available for a wide range of topics including summer and winter weather awareness and fire preparedness.

The City of Minot has also created a Program for Public Information Committee, creditable under Activity 330 of the Community Rating System program. This committee will discuss existing and future outreach programs, including those listed above. The above list does not include all public outreach actions being taken in the community. This goal is ongoing and future actions will consist of expanding the Program for Public Information and continuing the outreach currently in place.

Action 2: Join the National Fire Protection Agency’s Firewise Community Program

This is a new action included in the 2018 update to the Plan. The Firewise Community Program teaches residents and communities how they can prevent losses from wildfires. Educational information is available through the program to help citizens reduce the risk of wildfires at the local level. No other cities in North Dakota are currently participants in this program.

6.3.3	Goal 03: Protect Public Health and Safety Before, During, and After Hazard Events

Action 1: Work with state and federal partners to determine additional structural flood protection needs, and to design and construct those measures

The Mouse River Enhanced Flood Protection Project (MREFPP) began in 2013 and continuously evolves to fit the needs of Minot and surrounding communities. Collaborative efforts including the City of Minot, Ward County, the State of North Dakota, FEMA, USACE, and others, have proposed structural flood control projects for the entire Souris River Basin. Multiple phases of the projects within the city limits of Minot are currently under construction. This action is a long-term ongoing effort that will not be complete for several years.

Action 2: Purchase and install additional emergency power generators

Emergency power generators for six sanitary sewer lift stations have been added in the community. A Moderate/High priority level was assigned to this action because of its immediate impact on people and property in case of a flood.  This item is complete.

Action 3: Purchase and install additional warning sirens

A Moderate/High priority level was given to this action, as it is a mitigation strategy that applies to multiple hazards identified in the community. This action was completed in its entirety and will not be ongoing.

Action 4: Study and develop mitigation solutions to existing stormwater and drainage issues that currently result in periodic flooding

A City-wide storm water management plan has been developed as a guide for future projects to address areas with drainage problems. A new City ordinance was passed in 2013 which requires Storm Water Management Plans to be submitted for any proposed development within the jurisdictional limits of Minot. Drainage issues reported by residents are inspected at the site and recommendations are given to the homeowner or Public Works Department as applicable. This action has been completed and will be ongoing as part of this Plan.

Action 5: Install stream gauges to gather real-time data to better predict, prepare for, and respond to high water events in flood prone areas

This is a new action included in the 2018 Plan update. This action is most applicable to flood hazards, and has a moderate priority level. A stream gauge was added to the Broadway bridge over the Souris River in 2020 and is actively reporting water levels. This action is complete and maintenance of the gauge will be ongoing as a responsibility of the City Public Works Department.

6.3.4	Goal 04: Ensure Post-Disaster Operability of Critical Assets and Infrastructure.

Action 1: Develop GIS data regarding recent annexations and/or recently constructed assets, to provide for better hazard and risk mapping

The City’s GIS mapping system has been expanding as more information becomes available. Annexations of parcels into the City Limits are shown color-coded by year on the GIS map. A database of this information is also kept by the GIS Coordinator. Newly built or upgraded infrastructure including lift stations, sanitary sewer system facilities, and the City’s water supply system are also recorded on the GIS map. The collected data can be used in mitigation and emergency operations planning. This action is in progress and will be ongoing as part of the Plan.

6.3.5	Goal 05: Provide Long-Term Mitigation Solutions to Areas / Structures that Experience Repetitive Hazard Damage or Loss.

Action 1: Continue collection and storage of data regarding the vulnerabilities of public assets and infrastructure, to develop mitigation actions to better protect them.

Information about infrastructure and systems built or maintained by the City’s Public Works Department is regularly updated to provide an accurate depiction of the risks faced by these assets. Locations of these assets can be viewed on a map to determine which facilities are at risk for certain hazards. This action has been completed and will be ongoing as part of this Plan.

Action 2: Identify and acquire flood-prone properties throughout the City

Five repetitive loss properties in the City’s jurisdiction remain unmitigated. Many properties inundated by the Souris River in 2011 are being acquired by the City to use for flood storage areas or structural flood control measures. Information about these properties is available on the City’s GIS map and a master list is kept on the City’s internal computer servers. Homes on these properties are demolished or auctioned and relocated to prevent future damage from occurring. This is a long-term action item and is still in progress.

Action 3: Minot Water Treatment Plant Flood Protection Project

The Minot Water Treatment Plant area is a portion of the Mouse River Enhanced Flood Protection Plan (MREFPP), as discussed for Goal 3. Flood control structures around the Water Treatment Plant were completed prior to the 2018 Plan update. This action has already been completed so there will be no ongoing work.

Action 4: Phase MI-1 4th Ave Floodwall Project

Phase MI-1 is also included in the MREFPP and included in the 2018 Plan update as a new item. This phase of the flood control project is substantially completed and is expected to be fully completed in August 2022.

Action 5: Phase MI-2-3 Napa Valley Project - earthen levees starting at west edge of Minot

Levee construction began in 2018 on the west side of Minot as part of the MREFPP. This action is new in the 2018 update to the Plan. Phase MI-2-3 has been completed and the City took over operation and maintenance of the structures in September 2020.